## Cover & Instructions
SpinRise M01 – PR Module ¦ IST Checklist v1.1 with CR v1.5 traceability matrix
Prepared by IST: V. Palanivel
Document Code | KALSOFTE-IST-M01-PO-CHK-v1.1
Module | M01 – PR To PO Transfer
Source FSD | FSD v3.1
Development Owner | Abinandan
IST Lead | V. Palanivel (TL-IST)
IST Coordinator | M. Muthuvel
Build Drop (planned) | Friday 19 Jun 2026
IST Window | 19 Jun 2026 (Fri)
IST Clearance Target | EOD 19 Jun 2026 (Fri) — firm
Environment | SpinRise UAT / DB: KSP_M01_UAT (snapshot pre-IST)
Reporting Engine | QuestPDF (migrated from Crystal Reports)
Prep Deadline | EOD 19 Jun 2026 — PR To PO Transfer sheet populated and reviewer-signed
Transactions in Scope
# | Transaction | Primary Tester | Reviewer | Day-1 Focus | Day-2 Focus
1 | PR To Purchase Order | MuthuVel M | Palanivel V | Create / Save / Validate / Print | Regression + Mobile
How to Use This Workbook
1. Each transaction has its own sheet. Open the sheet for the transaction you are testing.
2. Populate the Test Case Header block first: Tester, Date, Build Label, Environment.
3. Execute test cases top-to-bottom. For each row, set Status = Pass / Fail / Blocked / N/A.
4. For every Fail or Blocked: log Defect ID, Severity (Critical/High/Medium/Low), and Evidence (screenshot / log path).
5. Regression anchors (Rec #16–#33 and IST Q1–Q18) are pre-listed at the end of each sheet — these MUST be re-verified.
6. Mobile Responsive section — SPRINT 2 TARGET (per Blueprint v6.1, CEO-confirmed). Complete if time permits. NOT a blocker for IST clearance in Sprint 1 (30-May pilot).
7. At end of Day 1 (26 May): Muthuvel consolidates Pass/Fail counts and shares status with TL-IST by 18:30 IST.
8. Day 2 (27 May): Re-test all defects, complete regression + mobile, IST sign-off by EOD.
9. No transaction is 'IST cleared' until: 100% Functional pass + 0 Critical/High open + Mobile section signed.
10. Sign-off block at the bottom of each sheet must be completed by Tester AND Reviewer before clearance.
Status Legend & Severity Definitions
Status | Meaning
Pass | Test step executed and observed result matches expected result.
Fail | Observed result deviates from expected; defect must be logged.
Blocked | Cannot execute due to dependency / environment / data issue.
N/A | Step not applicable for this build/scenario; justify in Remarks.
Severity | Definition
Critical | Blocks IST clearance. Data loss, security breach, system crash, financial impact.
High | Major functional break, no workaround, blocks downstream transaction.
Medium | Functional defect with workaround; affects usability but not data integrity.
Low | Cosmetic, label, alignment, minor UX; defer-able with note.

## 5. PR to PO Transfer
SpinRise M01 – PO Module ¦ IST Checklist v1.0 — PR to PO Transfer
SpinRise M01 — Field-wise · Flow-wise · Order Details / Tax-Discount / Payment / Instructions / Cancel-Status / Amendment / Approval / Delivery Schedule · CR v17-Jun-2026 Cross-Referenced
Transaction | PR to PO Transfer — Purchase Order > PR to PO Transfer (PO Header, Tax/Discount, Payment, Instructions, Cancel/Status, Amendment, Approval, Delivery Schedule)
Route | /po/transfer
FSD Baseline | M01 PO Module FSD v3.1 Final — CEO Countersigned 14-Jun-2026 (GST routing §5.6; Delivery Schedule §5.16, OQ-NEW Option B)
CR Baseline | SPINRISE_M01_PO_CR_17-Jun-2026 (CR-001 to CR-022) — pending CEO review and direction
Tester (Primary) | MuthuVel M
Reviewer | Palanivel V
Execution Date
Build Label | PR to PO Transfer — screenshot capture build, 18-Jun-2026
Environment / DB | SpinRise UAT / 172.16.16.40:3000 — SATHY SILKS (P) LTD (Unit - JAT TECHNO SPINTEX MILL) / KALSOFTE login
1. Page Load, Toolbar & Record Navigation
TC ID | Domain | Test Case Description | Pre-Condition / Data | Steps | Expected Result | Existing Status | Status | Defect ID | Severity | Evidence / Remarks | Tester | Date
POT-PL-01 | UX/UI | Breadcrumb shows 'Purchase Order > PR to PO Transfer' on landing | Login as KALSOFTE | Open Purchase Order → PR to PO Transfer → PR to PO Transfer (left nav) | Breadcrumb 'Purchase Order > PR to PO Transfer' visible in blue header bar; route /po/transfer | Open | Pass |  | Medium
POT-PL-02 | UX/UI | Top header band shows Company + Unit name centred (e.g., SATHY SILKS (P) LTD ( UNIT - JAT TECHNO SPINTEX MILL )) | On landing | Observe centre of top header | Company + Unit name displayed prominently, centred | Open | Pass |  | Low
POT-PL-03 | UX/UI | Top-right user chip shows logged-in user (KALSOFTE) with company badge (KALPATHARU SPINNERS PVT. LTD.) | Logged in as KALSOFTE | Observe top-right chip | User code + company name visible | Open | Pass |  | Low
POT-PL-04 | UX/UI | Left nav shows hierarchy Purchase Order > PR to PO Transfer > PR to PO Transfer, active item highlighted | On landing | Inspect left sidebar | Active menu item highlighted blue; parent nodes expanded | Open | Pass |  | Low
POT-PL-05 | UX/UI | Toolbar order: + New PO (F1) ¦ Find (F2) ¦ Delete (F3) ¦ Save (Ctrl+S) ¦ Cancel (F6) ¦ Print (F7) with keyboard hints | On landing | Visual verify toolbar | All six controls present, correct order, correct shortcut labels | Open | Pass |  | Medium
POT-PL-06 | Functional | On loading an existing PO, toolbar reflects View-mode state: Save disabled (greyed, 'Ctrl+S' hint still shown), New/Find/Delete/Print enabled, Cancel enabled | Open existing PO-001131 | Inspect toolbar button states | Save visually disabled; New, Find, Delete, Print, Cancel enabled | Open | Pass |  | Medium
POT-PL-07 | Functional | PO No. and tab strip persist correctly across all 7 tabs (Order Details/Tax-Discount/Payment/Instructions/Cancel-Status/Amendment/Approval) for the same record | Open PO-001131 | Click through all 7 tabs in sequence | PO No. (top-right, e.g., PO-001131), header band values, and footer KPI strip remain constant and correct across every tab | Open | Pass |  | High
POT-PL-08 | UX/UI | Top-right date chip shows the PO's transaction date (e.g., 18-Jun-2026), 'Created by' shows KALSOFTE, consistently on every tab | Open PO-001131 | Observe top-right date chip and Created by label on each tab | Same date and creator shown on all tabs; not the system/today date if record was created earlier | Open | Pass |  | Medium
POT-PL-09 | Functional | Record navigation arrows (« ‹ › ») move between POs correctly with correct disable state at list ends | ≥3 POs exist | Click «, ‹, ›, » in sequence | Loads first/previous/next/last PO respectively; « and ‹ disabled at first record, › and » disabled at last record | Open | Pass |  | Medium
POT-PL-10 | Functional | Navigating between POs via arrows refreshes ALL tabs' data (not just Order Details) without stale data from previous PO | Open PO A on Tax/Discount tab | Click › to move to PO B while on a non-default tab | Tab remains on Tax/Discount but all fields refresh to PO B's data; no residual PO A values | Open | Pass |  | Critical
POT-PL-11 | Functional | Footer KPI strip (Total Lines, Order Value, Total GST, Total Order Value, Approval Pipeline) recalculates correctly for the loaded PO on every tab | Open PO-001131 (1 line, Order Value 7.00, GST 1.26, Total 8.26) | Observe footer strip on each tab | Total Lines=1, Order Value=7.00 (Before GST), Total GST=1.26 (CGST+SGST/IGST), Total Order Value=₹8.26 (Incl. GST & TCS) consistently shown | Open | Pass |  | High
POT-PL-12 | UX/UI | Approval Pipeline footer widget shows correct current stage dot and status label (e.g., Requested / L1 / PENDING) | Open PO-001131 (Approval Status = PENDING) | Observe Approval Pipeline card in footer | Pipeline shows current stage highlighted (purple/active dot at 'Requested'), label 'PENDING' beneath L1 | Open | Pass |  | Medium
POT-PL-13 | Functional | Horizontal scrollbar on Item Details grid allows scrolling to view all line-level columns (Discount, Packing, Freight, Insurance, Other, GST, TCS, Landing Cost, and further right-hand columns) | PO with line item loaded | Drag horizontal scrollbar at bottom of grid fully right | All columns including ones beyond 'Landing Cost' (e.g., Total) become visible without column squeeze/overlap | Open | Pass |  | Medium
2. Order Details Tab — Header Fields
TC ID | Domain | Test Case Description | Pre-Condition / Data | Steps | Expected Result | Existing Status | Status | Defect ID | Severity | Evidence / Remarks | Tester | Date
POT-OD-01 | Functional | '+ New PO' (F2) switches form to Add mode with PO No. shown as auto-generate placeholder | View mode | Click + New PO or press F2 | Form switches to entry mode; PO No. field shows 'Auto-generated on save' or similar; Save/Cancel enabled | Open | Pass |  | High
POT-OD-02 | Field: PO Date | PO Date defaults to today's date (dd-MMM-yyyy) in New mode, editable via calendar picker | New mode | Inspect PO Date field; click calendar icon | Defaults to current date; picker opens with dd-MMM-yyyy format (e.g., 18-Jun-2026) | Open | Pass |  | Medium
POT-OD-03 | Field: Order Type | Order Type dropdown is mandatory (marked *); values include AD – ADVANCE PAY... (and other configured order types) | New mode | Open Order Type dropdown; attempt Save without selecting | All configured order types listed; Save blocked with validation if left blank | Open | Pass |  | Critical
POT-OD-04 | Field: Supplier | Supplier dropdown is mandatory (*); shows Supplier Code + Name (e.g., C1 0001 – DEVDEEP COTTON INDUSTRIES); searchable | New mode | Open Supplier dropdown; type partial name | List filters correctly; selecting a supplier auto-populates GSTIN and GST State | Open | Pass |  | Critical
POT-OD-05 | Field: GSTIN / GST State | On Supplier selection, GSTIN and GST State auto-populate from supplier/GST master and are read-only | Select Supplier C1 0001 – DEVDEEP COTTON INDUSTRIES | Observe GSTIN and GST State fields after selection | GSTIN shows e.g. 24AAAEFD8249C1Z0; GST State shows '24 - Gujarat'; fields not manually editable | Open | Pass |  | Critical
POT-OD-06 | Field: GSTIN / GST State (CR-006 cross-check) | Selecting a HOME-STATE supplier (same state as company) must clear BOTH IGST % and IGST amount to zero, not amount only; CGST/SGST populate per SP #9 (ksp_PO_GetGSTRouting) | PO header with a home-state supplier | Change Supplier from an inter-state supplier to a home-state supplier; inspect Tax/Discount and line GST split | IGST % field AND IGST amount both reset to 0.00; CGST/SGST recalculate and populate correctly across all line items | Open | Pass |  | Critical
POT-OD-07 | Field: Inspect | Inspect dropdown (Yes/No) is present and persists selection on save | New/Edit mode | Toggle Inspect to 'Yes', save, re-open | Value persists as selected ('Yes') | Open | Pass |  | Medium
POT-OD-08 | Field: Form Type | Form Type dropdown shows configured values (e.g., 03 – NONE) and persists on save | New/Edit mode | Open dropdown; select a value; save; re-open | Selected Form Type value persists and displays correctly | Open | Pass |  | Medium
POT-OD-09 | Field: Ref. No. / Ref. Date | Ref. No. (optional) and Ref. Date (optional, calendar picker) accept and persist values without forcing entry | New mode | Leave both blank; save | Save not blocked; fields remain blank/optional on re-open | Open | Pass |  | Low
POT-OD-10 | Field: Round Off | Round Off field accepts numeric entry (including negative for downward rounding) and feeds into Order Value calculation | Line items with non-round total | Enter a Round Off value; observe Order Value | Order Value field updates by exactly the Round Off amount entered | Open | Pass |  | High
POT-OD-11 | Field: Order Value (CR-004) | Order Value (₹) field is positioned immediately after Round Off in the header layout (not at the end of the row) | Order Details tab, any PO | Visually inspect field order after Round Off | Order Value field appears directly adjacent to/after Round Off per CR-004 | Open | Pass |  | Medium
POT-OD-12 | Field: Order Value | Order Value (₹) is read-only and recalculates automatically as line items, discount, tax, or round-off change | PO with 1 line, Value 7.00, GST 1.26 | Change line Quantity or Rate; observe Order Value | Order Value updates immediately to reflect new computed total (matches footer 'Total Order Value' card) | Open | Pass |  | Critical
POT-OD-13 | Field: Currency / Curr. Rate | Currency defaults to INR with Curr. Rate = 1.0000; selecting a foreign currency should enable Curr. Rate for entry | New mode | Change Currency dropdown to a foreign currency (if configured) | Curr. Rate field becomes editable; INR remains default for domestic POs | Open | Pass |  | Medium
POT-OD-14 | Field: Currency / Order Value (CR-005) | When a foreign/import currency is selected, an additional Order Value field in the selected billing currency should appear, auto-calculated using the Payment tab exchange rate | Foreign-currency PO | Select foreign currency; enter/observe Payment tab exchange rate; check header | New foreign-currency Order Value field appears and auto-calculates = INR Order Value / Curr. Rate (or per FSD formula) | Open | Fail |  | High
POT-OD-15 | Field: Remarks | Remarks (header) is optional free text, persists on save, no forced character limit issue | New/Edit mode | Enter long remarks text; save; re-open | Full text persists without truncation (within FSD-defined max length) | Open | Pass |  | Low
POT-OD-16 | Cross-field | Save blocked when any mandatory header field (Order Type, Supplier) is empty, with consolidated validation messages | New mode, mandatories blank | Click Save | All blank mandatory fields flagged; focus moves to first invalid field | Open | Pass |  | Critical
POT-OD-17 | Item Details grid | Item Details tab shows line columns: Item Id, Item Name, UOM, PR No, PR Date, Rate, Quantity, Value, Discount, Packing, Freight, Insurance, Other, GST, TCS, Landing Cost (and further right columns via scroll) | PO-001131 loaded | Inspect Item Details grid header row | All listed columns present in this order; Item Id is hyperlinked (e.g., 1204001) | Open | Pass |  | High
POT-OD-18 | Item Details grid | Item Id hyperlink in grid navigates to / previews the item master record | Line item present | Click Item Id link (e.g., 1204001) | Item master detail opens or previews (per FSD-defined behaviour) | Open | Pass |  | Medium
POT-OD-19 | Item Details grid | PR No. and PR Date columns correctly reflect the source PR that the line was transferred from | Line transferred from PR No. 75, PR Date 2026-06-05 | Inspect PR No / PR Date columns | Values match exactly the source PR (75, 2026-06-05) | Open | Pass |  | Critical
POT-OD-20 | Item Details grid | Value column = Rate × Quantity, recalculates instantly on either field's change | Line with Rate=7.0000, Qty=1.000 | Change Quantity to 2; observe Value | Value updates to 14.00 immediately | Open | Pass |  | High
3. Tax / Discount Tab
TC ID | Domain | Test Case Description | Pre-Condition / Data | Steps | Expected Result | Existing Status | Status | Defect ID | Severity | Evidence / Remarks | Tester | Date
POT-TD-01 | UX/UI | Tax/Discount tab renders three groups: Tax Rates, Deductions & Charges, Applicability — matching FSD §5.6 layout | Open Tax/Discount tab | Visual inspect section headers | 'TAX RATES', 'DEDUCTIONS & CHARGES', 'APPLICABILITY' all present with correct fields beneath each | Open | Pass |  | Medium
POT-TD-02 | Field: TCS % | TCS % field accepts decimal entry and feeds into line-level TCS Amount and Total Order Value | Line items present | Enter TCS % = 1; observe line TCS Amount and footer Total Order Value | TCS Amount recalculates per line; Total Order Value (Incl. GST & TCS) updates accordingly | Open | Pass |  | High
POT-TD-03 | Field: FCA / FOB | FCA / FOB numeric field present and persists entered value on save | Edit mode | Enter a value; save; re-open | Value persists exactly as entered | Open | Pass |  | Low
POT-TD-04 | Field: File No. | File No. text field is optional and persists on save without validation blocking | Edit mode | Leave blank; save | Save not blocked; field remains blank | Open | Pass |  | Low
POT-TD-05 | Field: Discount | Discount % and Discount Amount (₹) fields are linked — entering % auto-computes Amount and vice versa | Header Discount section | Enter Discount % = 5; observe Amount field; clear and enter Amount instead | Both directions of calculation work correctly and consistently against the order base | Open | Pass |  | High
POT-TD-06 | Field: Discount Amount sign (CR-022) | Discount Amount must display as a POSITIVE number on screen (no leading negative sign), even though it reduces the order value internally | Discount applied to an order | Enter a discount; inspect displayed Discount Amount value (header and line grid) | Discount Amount shows as positive figure (e.g., '35.00', not '-35.00') per CR-022 | Open | Pass |  | Medium
POT-TD-07 | Field: Packing | Packing % and Packing Amount (₹) fields linked bidirectionally like Discount; affects Landing Cost when 'Before Tax'/'Before Duty' as applicable | Header Packing section | Enter Packing % = 2; observe Amount and Landing Cost impact on line items | Packing Amount computes correctly; Landing Cost reflects packing per Applicability settings | Open | Fail |  | High
POT-TD-08 | Field: Freight (CR-009) | Freight Amount entry must NOT auto-calculate/override Freight %; reverse calculation (Amount → %) must work the same way Discount and Packing do | Header Freight section, order base known | Enter Freight Amount directly (not %); observe Freight % field | Freight % auto-derives consistently from the entered Amount, matching the same bidirectional behaviour as Discount/Packing (per CR-009 — currently a known defect where Amount entry doesn't auto-calc %) | Open | Fail |  | High
POT-TD-09 | Field: Insurance | Insurance % and Amount fields linked bidirectionally; Insurance Position (Before/After Duty) affects calculation base | Header Insurance section | Toggle Insurance Position between Before Duty / After Duty; enter a value | Calculated Insurance Amount changes appropriately based on position toggle | Open | Fail |  | Medium
POT-TD-10 | Field: Cess | Cess % and Amount fields linked bidirectionally; Cess Position (Before/After Tax) affects calculation base | Header Cess section | Toggle Cess Position; enter a value | Cess Amount recalculates per the selected position basis | Open | Fail |  | Medium
POT-TD-11 | Applicability: Freight Payment | Freight Payment radio (Paid / To Pay) is selectable and persists; affects whether freight is included in supplier-payable Order Value | New/Edit mode | Toggle between Paid and To Pay; save; re-open | Selection persists; Order Value / payment computation reflects the chosen mode per FSD | Open | Pass |  | Medium
POT-TD-12 | Applicability: Freight/Discount/Packing/Insurance/Cess Position toggles | Each Before Tax/After Tax (or Before/After Duty) radio toggle correctly changes the calculation base used for that charge | New/Edit mode, line items present | Toggle each radio individually; observe recalculated GST and Landing Cost | Tax computation base shifts correctly per toggle (e.g., 'Before Tax' includes the charge in the GST-assessable value; 'After Tax' excludes it) | Open | Pass |  | Critical
POT-TD-13 | Applicability: Excise Include Packing | Excise Include Packing Yes/No toggle is present, selectable, and persists on save | New/Edit mode | Toggle Yes then No; save each; re-open | Selected value persists correctly across saves | Open | Pass |  | Low
POT-TD-14 (CR-010) | Functional | Toggling the Before/After Tax flag for any charge must trigger automatic GST recalculation (CGST/SGST/IGST) on all affected line items — currently a known defect where recalculation does not fire | Line items with GST already computed | Toggle a Before Tax/After Tax radio (e.g., Discount Application) | CGST/SGST/IGST values on the line grid recalculate immediately to reflect the new assessable base, without requiring a manual save/reload | Open | Pass |  | Critical
POT-TD-15 (CR-012) | Functional | Changing Discount or Freight % or Amount must trigger an IMMEDIATE recalculation of CGST/SGST/IGST against the revised assessable base — currently a known defect where this does not update | Line items with GST computed | Change Discount % from 0 to 5; observe line GST columns without clicking elsewhere | CGST/SGST/IGST update instantly to the new base reflecting the discount adjustment | Open | Pass |  | Critical
POT-TD-16 (CR-011b) | Functional | Discount, Freight, and Other Amount fields directly on the Item Details GST/line grid must be editable and trigger GST/Landing Cost recalculation when changed at line level (not just header level) | Line item grid, GST window open | Edit Discount/Freight/Other Amount directly on a line; tab out | Line recalculates GST and Landing Cost immediately based on the edited line-level value | Open | Pass |  | Critical
POT-TD-17 (CR-013) | Functional | Rate and Quantity fields must be directly editable within the GST window/line grid, triggering recalculation of assessable value, charges, and GST components | GST window / line grid open | Edit Rate or Quantity directly in this view | Assessable Value, all charge amounts, and GST components recompute correctly and immediately | Open | Pass |  | Critical
POT-TD-18 (CR-011a) | Functional / Scope | Additional Tax field (if present in GST window) is removed per CR-011a — confirm it is out of Sprint 1 scope and not rendered | GST window | Inspect GST window for an 'Additional Tax' field | Field absent (removed); no orphaned UI control or broken layout where it used to sit | Open | Closed |  | Low
POT-TD-19 | Line grid GST columns | Line grid displays GST, TCS, and Landing Cost columns matching header-level tax configuration; Landing Cost = Value + all applicable charges + GST + TCS per FSD formula | Line item, Value=7.00, GST=1.26, TCS=0.00 | Inspect Landing Cost = 8.26 | Landing Cost correctly equals Value + GST + TCS (+ other applicable charges) = 8.26 | Open | Pass |  | Critical
POT-TD-20 (CR-008) | UX/UI | Item line grid charge-column sequence must be: Discount → Packing → Freight → Insurance → Other → GST → TCS Amount → Landing Cost (Landing Cost last, after TCS) | Item Details/Tax-Discount grid | Scroll grid fully right; inspect column order | Exact column order matches CR-008 specification; Landing Cost is the rightmost charge-related column | Open | Pass |  | Medium
4. Payment Tab
TC ID | Domain | Test Case Description | Pre-Condition / Data | Steps | Expected Result | Existing Status | Status | Defect ID | Severity | Evidence / Remarks | Tester | Date
POT-PM-01 | UX/UI | Payment Mode radio shows two options: Direct and Through Bank, with Direct selected by default for new POs | New mode | Inspect Payment Mode radios on a new PO | 'Direct' pre-selected; 'Through Bank' selectable | Open | Pass |  | Low
POT-PM-02 | Functional | Selecting 'Direct' enables Direct Instruction, Advance Amount, Mode of Payment, Payment Ref., Ref. Date fields for entry | Payment tab, Direct selected | Inspect/enter values into each field | All five fields editable and accept appropriate input types (text/number/dropdown/date) | Open | Pass |  | Medium
POT-PM-03 | Functional | Selecting 'Through Bank' changes the visible/required field set appropriately (e.g., bank details) per FSD, distinct from Direct mode fields | Payment tab | Toggle to Through Bank | Field set updates to bank-relevant fields per FSD; Direct-only fields hidden or disabled appropriately | Open | Pass |  | Medium
POT-PM-04 | Field: Advance Amount | Advance Amount accepts numeric entry, defaults to 0.00, and cannot exceed PO Order Value (validation per FSD) | Payment tab, Order Value = 8.26 | Enter Advance Amount greater than Order Value | Validation blocks save or shows warning that advance exceeds order value (if such a rule exists in FSD; otherwise confirm actual behaviour against FSD) | Open | Fail |  | High
POT-PM-05 | Field: Mode of Payment | Mode of Payment dropdown shows configured payment modes and persists selected value on save | Edit mode | Select a Mode of Payment; save; re-open | Selected mode persists and displays correctly | Open | Pass |  | Medium
POT-PM-06 | Field: Payment Ref. / Ref. Date | Payment Ref. (text) and Ref. Date (calendar) are optional, accept entry, and persist on save | Edit mode | Enter both fields; save; re-open | Both values persist exactly as entered | Open | Pass |  | Low
POT-PM-07 | Cross-tab | Payment tab's exchange-rate-relevant fields correctly feed the foreign-currency Order Value calculation referenced in Order Details (CR-005) when a non-INR currency is selected | Foreign-currency PO | Set currency to non-INR on Order Details; check Payment tab for exchange rate input; change rate | Header foreign-currency Order Value recalculates per the rate entered on Payment tab | Open | Pass |  | High
POT-PM-08 | Functional | Payment Mode and field values persist correctly when navigating away to another tab and back, without resetting to default | Enter Payment data | Fill Payment tab; switch to Order Details tab; switch back to Payment | All previously entered Payment values remain exactly as entered (not reset to Direct/blank) | Open | Pass |  | High
5. Instructions Tab
TC ID | Domain | Test Case Description | Pre-Condition / Data | Steps | Expected Result | Existing Status | Status | Defect ID | Severity | Evidence / Remarks | Tester | Date
POT-IN-01 | Field: Carrier | Carrier is mandatory (*); dropdown shows code + name (e.g., 0007 – OCEAN BRIDGHE CARRIER); defaults to a configured default carrier ('Courier') | New mode | Open Carrier dropdown; inspect default value | Default carrier pre-selected (e.g., 'Courier'); full list of carriers with code+name shown on open | Open | Pass |  | High
POT-IN-02 (CR-020) | Field: Carrier | A blank/clear option must be available in the Carrier dropdown alongside the existing default, allowing the user to deliberately leave Carrier unselected | Carrier dropdown open | Open Carrier dropdown; look for a blank/clear entry | A blank or '— Clear —' option exists in the list, separate from the 'Courier' default, per CR-020 | Open | Pass |  | Medium
POT-IN-03 | Field: Carrier | Save blocked when Carrier is left blank (mandatory field), consolidated validation fires | New mode, Carrier cleared | Clear Carrier; click Save | Save blocked; Carrier field flagged as required | Open | Pass |  | Critical
POT-IN-04 | Field: Delivery Location | Delivery Location dropdown is optional, lists configured delivery locations, and persists selected value on save | Edit mode | Select a Delivery Location; save; re-open | Selected value persists and displays correctly | Open | Pass |  | Medium
POT-IN-05 | Field: Billing Address | Billing Address dropdown is optional, lists configured billing addresses, and persists on save | Edit mode | Select Billing Address; save; re-open | Value persists correctly | Open | Pass |  | Medium
POT-IN-06 | Field: Credit Days | Credit Days numeric field defaults to 0, accepts positive integers, and feeds into payment-due-date logic if applicable per FSD | New mode | Enter Credit Days = 30; save; re-open | Value persists as 30; any dependent due-date computation (if specified in FSD) reflects this | Open | Pass |  | Medium
POT-IN-07 | Field: Delivery Date | Delivery Date (header-level) defaults to today and is independently editable from the line-level Delivery Schedule dates | New mode | Inspect default; change to a future date | Defaults to today (dd-MMM-yyyy); changing it does not silently overwrite per-line Delivery Schedule dates that may already be set | Open | Pass |  | Medium
POT-IN-08 | Field: Special Instruction | Special Instruction free-text field is optional, accepts multi-word input, and persists on save without truncation | Edit mode | Enter a sentence-length instruction; save; re-open | Full text persists; no character cap issue observed within FSD-allowed length | Open | Pass |  | Low
POT-IN-09 | Field: Despatch / Purpose / Other Levies | Despatch, Purpose, and Other Levies fields are optional, accept entry, and persist independently of each other | Edit mode | Enter distinct values in each of the three fields; save; re-open | All three values persist correctly and independently (no cross-field overwrite) | Open | Pass |  | Low
POT-IN-10 | Field: Pricing Terms | Pricing Terms dropdown lists configured terms (e.g., Ex-Works, FOB, CIF as applicable) and persists selection on save | Edit mode | Select a Pricing Terms value; save; re-open | Selected term persists and displays correctly | Open | Pass |  | Medium
POT-IN-11 | Field: Packing & Forwarding / Insurance / Freight (Instructions tab) | Packing & Forwarding, Insurance, and Freight free-text/numeric fields on Instructions tab are distinct from the Tax/Discount tab's Packing/Insurance/Freight % and Amount fields, and do not overwrite them | Edit Tax/Discount %, then edit Instructions tab equivalents | Set Packing % on Tax/Discount; then enter text in Instructions' Packing & Forwarding field; verify Tax/Discount value unchanged | Tax/Discount tab's numeric Packing % value remains unchanged after editing the Instructions tab's separate field | Open | Pass |  | High
6. Cancel / Status Tab
TC ID | Domain | Test Case Description | Pre-Condition / Data | Steps | Expected Result | Existing Status | Status | Defect ID | Severity | Evidence / Remarks | Tester | Date
POT-CS-01 | UX/UI | Cancel/Status tab shows Reminder, Status, Cancellation Date, Reason, Approved (Y/N dropdown), Approved By fields | Open Cancel/Status tab | Inspect field layout | All six fields present and laid out as in current build (per Image 4) | Open | Pass |  | Medium
POT-CS-02 | Field: Cancelled checkbox | Cancelled checkbox is unchecked by default for an active PO and, when checked, should require Cancellation Date and Reason before save | Active PO, Cancelled unchecked | Check 'Cancelled'; attempt Save without Cancellation Date/Reason | Save blocked until Cancellation Date and Reason are provided (per cancellation business rule) | Open | Fail |  | Critical
POT-CS-03 | Field: Approved (cancellation) | Approved dropdown defaults to 'N'; changing to 'Y' should require Approved By to be populated | Cancellation in progress | Set Approved = Y without entering Approved By | Validation requires Approved By when Approved = Y (per FSD cancellation approval rule) | Open | Fail |  | High
POT-CS-04 | Field: Reason | Cancellation Reason is mandatory once Cancelled is checked; free text persists on save | Cancelled checked | Leave Reason blank; attempt save | Save blocked; Reason flagged as required when cancellation is in progress | Open | Fail |  | Critical
POT-CS-05 | Functional | Cancelling a PO that already has GRN/Invoice activity against it should be blocked or warned per FSD downstream-impact rule | PO with linked GRN/Invoice (if test data available) | Attempt to cancel such a PO | Cancellation blocked with explanatory message, OR explicit warning of downstream impact, per FSD; must not silently cancel a PO with live downstream transactions | Open | Fail |  | Critical
POT-CS-06 | Functional | Once a PO is marked Cancelled, the toolbar's Save/Modify-equivalent actions for that record are restricted appropriately (e.g., line items become read-only) consistent with cancelled-state rules used elsewhere (PR Cancellation precedent) | PO cancelled and saved | Re-open the cancelled PO; attempt to edit a line item | Line items / header fields render read-only or edits are blocked, consistent with Cancelled state | Open | Fail |  | High
POT-CS-07 | Field: Status | Status field (read-only display, distinct from Approval Status on Approval tab) correctly reflects the PO's overall lifecycle state | PO in various states (Requested/Cancelled/Approved) | Inspect Status field value against actual PO state | Status value accurately matches the PO's true lifecycle stage at all times | Open | Fail |  | Medium
POT-CS-08 | Field: Reminder | Reminder field (date/text per its control type) is optional and persists on save without affecting any other tab's data | Edit mode | Enter a Reminder value; save; re-open; check other tabs unaffected | Reminder value persists; no cross-tab data corruption observed | Open | Fail |  | Low
POT-CS-09 | Functional | Un-cancelling (unchecking Cancelled after it was saved as cancelled) is either explicitly blocked per FSD or requires a defined reversal workflow — must not silently flip back | Previously cancelled PO | Open cancelled PO; attempt to uncheck Cancelled and save | Per FSD: either reversal is blocked entirely, or a defined re-activation rule/approval is enforced — confirm actual behaviour against FSD and flag any silent/unguarded reversal as a defect | Open | Fail |  | Critical
7. Amendment Tab
TC ID | Domain | Test Case Description | Pre-Condition / Data | Steps | Expected Result | Existing Status | Status | Defect ID | Severity | Evidence / Remarks | Tester | Date
POT-AM-01 | UX/UI | Amendment tab shows AMD Order No., AMD Date, Ref. Order No., Ref. Date fields, all showing '—'/blank placeholders when no amendment exists | PO with no amendments (PO-001131) | Open Amendment tab | All four fields show placeholder dash/blank; message 'No amendments raised. Amendment history will appear here once an amendment is created.' displayed | Open | Pass |  | Low
POT-AM-02 | Functional | Creating an amendment against this PO generates a new AMD Order No. and AMD Date, while Ref. Order No./Ref. Date point back to the original PO | No prior amendments | Trigger an amendment workflow (if accessible from this screen or a linked screen) and save | AMD Order No. auto-generated distinct from original PO No.; Ref. Order No. = original PO No.; Ref. Date = original PO Date | Open | Pass |  | Critical
POT-AM-03 | Functional | Once an amendment exists, the 'No amendments raised' placeholder message is replaced by actual amendment history rows (date, what changed, by whom) | PO with ≥1 amendment | Open Amendment tab on an amended PO | Amendment history grid/list populated with the relevant amendment record(s); placeholder message no longer shown | Open | Pass |  | High
POT-AM-04 | Functional | Item Details and Delivery Schedule grids on the Amendment tab reflect the data as it stood at/after the amendment, consistent with the rest of the PO record | Amended PO | Compare Item Details grid values on Amendment tab vs Order Details tab for the same PO | Both tabs show identical, consistent line-item data for the same PO (no divergence between tabs) | Open | Pass |  | Medium
POT-AM-05 | Functional | Amendment of a Cancelled PO is blocked, consistent with the Cancel/Status tab's lifecycle rules | Cancelled PO | Attempt to raise an amendment against a cancelled PO | Amendment action blocked or unavailable for cancelled POs | Open | Fail |  | High
POT-AM-06 | Functional | Multiple sequential amendments on the same PO are each tracked distinctly (AMD Order No. increments / is uniquely identified per amendment), not overwritten | PO amended twice | Raise a second amendment after the first; inspect Amendment tab | Both amendment records are distinctly tracked/visible; second amendment does not erase the first's history | Open | Fail |  | High
8. Approval Tab
TC ID | Domain | Test Case Description | Pre-Condition / Data | Steps | Expected Result | Existing Status | Status | Defect ID | Severity | Evidence / Remarks | Tester | Date
POT-AP-01 | UX/UI | Approval tab header shows Approval Status (e.g., PENDING), Print Status (e.g., Not Printed), Created By, Created On | Open PO-001131 Approval tab | Inspect header fields | Approval Status='PENDING', Print Status='Not Printed', Created By='KALSOFTE', Created On='18-Jun-2026' — matches Image 2 | Open | Pass |  | Medium
POT-AP-02 | Functional | Approval Status badge colour reflects state distinctly (e.g., amber/orange for PENDING, green for Approved, red for Declined) consistent with PR module's status-badge conventions | POs in different approval states | Open POs in Pending / Approved / Declined states; compare badge colours | Each state has a visually distinct, consistent badge colour across the module | Open | Pass |  | Medium
POT-AP-03 | Functional | Print Status flips from 'Not Printed' to 'Printed' (with timestamp/user if applicable) once the PO has been printed via the Print toolbar action | PO not yet printed | Click Print (F7); complete print/preview; return to Approval tab | Print Status updates to 'Printed' (or equivalent) reflecting the actual print action | Open | Pass |  | Medium
POT-AP-04 | Functional | Approval tab's Item Details sub-tab shows identical line data (Item Id, Item Name, UOM, PR No, PR Date, Rate, Quantity, Value, Discount...Landing Cost) as the Order Details tab for the same PO | Open PO-001131, compare Approval > Item Details vs Order Details | Switch between Order Details and Approval tabs; compare Item Details grids | Line data is identical and consistent between both tabs for the same PO | Open | Pass |  | High
POT-AP-05 | Functional | Approval action(s) available to an authorised approver (Approve/Decline/Hold, etc., per FSD's approval level design) are present and gated by user role | Login as an approver-role user vs a non-approver | Open Approval tab as each role | Approval action controls visible/enabled only for users with approval authority at the current pending level; hidden/disabled for others | Open | Fail |  | Critical
POT-AP-06 | Functional | Approving the PO transitions Approval Status from PENDING to the next defined state and updates the footer Approval Pipeline widget's active stage accordingly | PO pending at L1 | Perform Approve action as L1 approver | Approval Status updates (e.g., to next level or Approved); pipeline widget advances to next stage dot | Open | Fail |  | Critical
POT-AP-07 | Functional | Declining/Holding the PO at any approval level records the action with a reason (if FSD requires it) and updates Approval Status + Pipeline accordingly, without silently reverting prior-level approvals (consistent with FSD's audit-history-preservation principle for the parallel PO Approval module) | PO pending at L2 after L1 approved | Decline at L2 with a reason | Approval Status reflects Declined; L1's prior approval remains historically recorded (not erased); pipeline reflects Decline at L2 | Open | Fail |  | Critical
POT-AP-08 | Functional | Created By and Created On values on the Approval tab match the original PO creation metadata exactly across all tabs (no divergence from Order Details tab's equivalent values) | PO-001131 | Compare Created By/On between Approval tab and Order Details tab header | Identical user and timestamp shown on both | Open | Pass |  | Medium
POT-DS-01 | UX/UI | Delivery Schedule sub-tab grid shows columns: # ¦ Item Id ¦ Item Name ¦ PR No. ¦ UOM ¦ PO Qty ¦ Scheduled Qty ¦ Balance Qty ¦ Delivery Date ¦ Remarks | Open PO-001131 > Delivery Schedule sub-tab | Inspect grid header | All 10 columns present in this exact order, matching Image 1/8 | Open | Pass |  | Medium
POT-DS-02 | Functional | Hint text 'Add unlimited delivery rows per item · Σ Scheduled Qty must equal PO Qty per item' is displayed and the underlying rule is enforced on save | Delivery Schedule sub-tab | Inspect hint text; attempt to save with Σ Scheduled Qty ≠ PO Qty for a line | Hint text visible; Save blocked (or warning shown) when the sum of Scheduled Qty across delivery rows for an item does not equal that item's PO Qty | Open | Pass |  | Critical
POT-DS-03 | Functional | Balance Qty = PO Qty − Σ Scheduled Qty for that item, recalculates live as Scheduled Qty rows are added/edited | Line: PO Qty=1.000, Scheduled Qty=1.000 | Inspect Balance Qty value (0.000) | Balance Qty correctly shows 0.000; changing Scheduled Qty to 0.5 updates Balance Qty to 0.500 immediately | Open | Pass |  | Critical
POT-DS-04 | Functional | Footer totals row (Σ Totals) sums PO Qty and Scheduled Qty columns correctly across all delivery rows/items, and shows a reconciliation message (e.g., 'Reconciled · PO: 1.000 = Sched: 1.000') | Multiple delivery rows across multiple items | Inspect Σ Totals footer row | Totals match the sum of all rows exactly; reconciliation message shows 'Reconciled' in green when PO Qty total = Scheduled Qty total | Open | Pass |  | Critical
POT-DS-05 | Functional | When Σ Scheduled Qty across all items does NOT equal Σ PO Qty, the reconciliation message changes from 'Reconciled' (green) to an unreconciled/warning state (per FSD §5.16 OQ-NEW Option B) | Add a delivery row with Scheduled Qty < PO Qty for an item, leaving balance unallocated | Inspect Σ Totals reconciliation message | Message changes to a non-green/warning state (e.g., 'Unreconciled · PO: X ≠ Sched: Y') reflecting the actual mismatch | Open | Pass |  | Critical
POT-DS-06 | Functional | 'Add unlimited delivery rows per item' — user can add multiple delivery schedule rows for the SAME item (split deliveries across dates) without a hard row-count cap | Item with PO Qty = 10 | Add 3+ delivery rows for the same item, splitting Scheduled Qty across them (e.g., 4 + 3 + 3) | All rows accepted; no artificial limit on row count per item; Σ Scheduled Qty across the rows can be validated against PO Qty=10 | Open | Pass |  | High
POT-DS-07 | Field: Delivery Date (per row) | Each delivery schedule row has its own independently editable Delivery Date via calendar picker, distinct from the Instructions tab's header-level Delivery Date | Delivery Schedule sub-tab | Edit Delivery Date on one row; verify Instructions tab's header Delivery Date is unaffected | Row-level Delivery Date changes independently; Instructions tab's header Delivery Date remains unchanged | Open | Pass |  | Medium
POT-DS-08 | Field: Delivery Date validation | Delivery Date per row cannot be earlier than the PO Date (per general FSD date-sequencing convention used elsewhere in the module) | Row with PO Date = 18-Jun-2026 | Attempt to set a row's Delivery Date earlier than 18-Jun-2026 | Save blocked or validation warning shown for a delivery date preceding the PO Date | Open | Pass |  | High
POT-DS-09 | Field: Remarks (per row) | Remarks field per delivery row is optional free text and persists independently per row on save | Multiple delivery rows | Enter distinct remarks on two different rows; save; re-open | Each row retains its own distinct Remarks value; no cross-row overwrite | Open | Pass |  | Low
POT-DS-10 | Functional | Scheduled Qty field is directly editable inline in the grid (not a separate modal) and immediately triggers Balance Qty and Σ Totals recalculation | Delivery Schedule grid | Edit Scheduled Qty inline on a row | Value updates inline; Balance Qty and footer Σ Totals recalculate without needing to save first | Open | Pass |  | High
POT-DS-11 | Functional (CR-015 cross-check) | Delivery Schedule grid does NOT show a retired 'Slot' column (4-slot model removed per CR-015, CEO-confirmed FSD v3.1 §5.16, Option B) | Delivery Schedule sub-tab, any PO | Inspect full column list (including scrolled-right columns) | No 'Slot' column present anywhere in the grid; field order matches the CR-015 approved list exactly (#, Item Id, Item Name, PR No., UOM, PO Qty, Scheduled Qty, Balance Qty, Delivery Date, Remarks) | Open | Pass |  | Medium
POT-DS-12 | Functional | Adding a new line item on the Order Details tab automatically creates a corresponding (initially unscheduled) row on the Delivery Schedule sub-tab for that item | Add a new line item via Item Details tab | Add a new item line; switch to Delivery Schedule sub-tab | New item appears in Delivery Schedule grid with PO Qty populated and Scheduled Qty/Balance Qty defaulting appropriately (e.g., Scheduled=0, Balance=PO Qty) | Open | Pass |  | Critical
POT-DS-13 | Functional | Deleting a line item from Item Details correspondingly removes/invalidates its Delivery Schedule row(s), without leaving an orphaned schedule row | Item with existing delivery schedule rows | Delete the item line from Item Details tab | Corresponding Delivery Schedule row(s) for that item are removed; no orphaned/dangling schedule data remains | Open | Pass |  | High
9. Cross-Tab Data Integrity & End-to-End Flow
TC ID | Domain | Test Case Description | Pre-Condition / Data | Steps | Expected Result | Existing Status | Status | Defect ID | Severity | Evidence / Remarks | Tester | Date
POT-E2E-01 | Flow | Create New PO end-to-end: New → fill Order Details (Order Type, Supplier) → add line item(s) → set Tax/Discount → set Payment → set Instructions (Carrier) → set Delivery Schedule (reconciled) → Save | Fresh New PO mode | Complete all 7 tabs in sequence as listed, then Save | PO saves successfully with a new PO No.; all entered values across every tab persist correctly on re-open; footer KPIs reflect final totals | Open | Pass |  | Critical
POT-E2E-02 | Flow | Save is blocked end-to-end if Delivery Schedule is NOT reconciled (Σ Scheduled Qty ≠ PO Qty for any item), even if all other tabs are valid | All tabs valid except Delivery Schedule unreconciled | Attempt Save | Save blocked specifically due to unreconciled Delivery Schedule; error message identifies the affected item(s) | Open | Pass |  | Critical
POT-E2E-03 | Flow | Modify an existing PO: change Supplier (home-state ↔ inter-state) and verify GST split (CGST/SGST ↔ IGST), Tax/Discount charges, Landing Cost, and footer Total GST/Total Order Value all update consistently across every tab | Existing PO with inter-state supplier | Change Supplier to a home-state supplier; save | IGST clears to 0 (CR-006), CGST/SGST populate, Landing Cost and footer totals recompute consistently; values match across Order Details, Tax/Discount, and Approval > Item Details | Open | Pass |  | Critical
POT-E2E-04 | Flow | Print a saved PO and verify the printed/PDF output reflects Order Details, Tax/Discount charges, Delivery Schedule, and Created By (full name, not user code) consistently with the on-screen data | Saved PO | Click Print (F7); inspect output | Printed output matches on-screen values for header, line items, charges, GST, and delivery schedule; Created By shows full user name per CR-021 | Open | Pass |  | High
POT-E2E-05 | Flow | Cancel a PO that has no downstream GRN/Invoice, then confirm Cancel/Status, Approval, and footer KPI all reflect the cancelled state consistently | Active PO, no downstream activity | Cancel via Cancel/Status tab with Reason; save | Cancelled=true persists; Status reflects Cancelled; Approval tab and footer remain internally consistent (no contradictory 'Pending' approval shown for a cancelled PO) | Open | Pass |  | High
POT-E2E-06 | Flow | Amend a saved PO (change a line Quantity), and verify the amendment is reflected consistently in Order Details, Approval > Item Details, and Delivery Schedule (Balance Qty/reconciliation) without breaking prior reconciliation | Saved, reconciled PO | Amend a line's Quantity upward; save amendment | New AMD Order No. created; Delivery Schedule's PO Qty for that item updates; reconciliation status re-evaluates (may go unreconciled until Scheduled Qty is adjusted) — confirm this is flagged, not silently ignored | Open | Pass |  | Critical
POT-E2E-07 | Flow | Navigating away from an unsaved PO (any tab, any field dirty) prompts a confirm-discard dialog before navigation proceeds | Dirty/unsaved changes on any tab | Make an edit; click Cancel (F6) or navigate via record-nav arrows | Confirm dialog appears warning of unsaved changes; proceeding discards changes, cancelling navigation preserves them | Open | Pass |  | High
10. Regression Anchors — Cross-Module Patterns to Re-Verify
TC ID | Domain | Test Case Description | Pre-Condition / Data | Steps | Expected Result | Existing Status | Status | Defect ID | Severity | Evidence / Remarks | Tester | Date
POT-REG-01 | Regression | Created By must show full user name (not user code) consistently — re-verify on PO header, Approval tab, and Print output (pattern from CR-PR-10 / CR-021) | Any PO, any tab showing Created By | Inspect Created By across Order Details, Approval, and Print output | Full name shown consistently in all three locations; no 'KSL'/code-only regression | Open | Pass |  | High
POT-REG-02 | Regression | Indian number formatting (lakh/crore grouping) applied consistently to all monetary fields across every PO tab and Print output (pattern from PR module IL-13/PR-20) | PO with values >1 lakh (if test data available) | Inspect monetary fields across all tabs and Print | Consistent Indian digit grouping throughout; no plain Western grouping regression | Open | Pass |  | Medium
POT-REG-03 | Regression | 4-decimal-place display for Rate fields enforced consistently across Order Details grid, Tax/Discount grid, and Print output (pattern from CR-PR-17 / IL-10) | Line item with Rate=7.0000 | Inspect Rate display across all relevant tabs and Print | Rate shows exactly 4 decimal places everywhere it appears | Open | Pass |  | Medium
POT-REG-04 | Regression | No screen flicker/blink on grid hover (Item Id column, line action icons) across PO tabs, consistent with CR-PR-07 fix applied on PR Form | Any PO with line items | Hover over grid rows and action icons for 3+ seconds on each tab | No flicker/blink observed; hover state stable | Open | Pass |  | Medium
POT-REG-05 | Regression | Save/action success toast renders on-screen (not in browser address bar) and persists ≥5 seconds, consistent with CEO directive applied across PR module (SV-09, FC-EX-08) | Save a PO successfully | Observe toast after Save | On-screen toast appears with success message; persists ≥5 sec or until dismissed; never in address bar | Open | Pass |  | High
POT-REG-06 | Regression | No JavaScript console errors on page load or after switching between any of the 7 PO tabs | Browser dev tools open | Load PO to PO Transfer screen; click through every tab | Zero console errors throughout | Open | Pass |  | Medium
POT-REG-07 | Regression | Session timeout while on PR to PO Transfer screen — re-login redirects back to /po/transfer, not to dashboard (pattern from FC-REG-08) | Simulate session expiry on this screen | Allow session to expire; re-login | Redirects to /po/transfer after re-authentication | Open | Pass |  | Low
11. Mobile Responsive — SPRINT 2 (Deferred, NOT a Sprint 1 Blocker)
TC ID | Domain | Test Case Description | Pre-Condition / Data | Steps | Expected Result | Existing Status | Status | Defect ID | Severity | Evidence / Remarks | Tester | Date
POT-MB-01 | Mobile | PR to PO Transfer screen loads without horizontal scroll on 375px viewport for the header and toolbar region | Sprint 2 build; 375px viewport | Load screen at 375px width | No horizontal overflow on header/toolbar; grid remains independently scrollable |  | N/A |  | Low
POT-MB-02 | Mobile | All 7 tabs (Order Details...Approval) remain individually accessible via a mobile-appropriate tab control (scrollable tab strip or dropdown) at 375px | Sprint 2 build; mobile viewport | Inspect tab navigation at 375px | Tabs accessible without being cut off or hidden; no tab permanently inaccessible |  | N/A |  | Low
POT-MB-03 | Mobile | Delivery Schedule grid (10 columns) is usable on mobile via horizontal scroll or a card-based responsive layout, without breaking the Σ Totals reconciliation footer | Sprint 2 build; mobile viewport | Open Delivery Schedule sub-tab at 375px | Grid is usable (scrollable or restructured); reconciliation footer remains visible and accurate |  | N/A |  | Medium
SIGN-OFF
Role | Name |  | Signature |  | Date |  | Remarks
Tester | V. Palanivel
Reviewer / TL-IST | V. Palanivel
IST Co-ord | M. Muthuvel